## Sheet1
Intended Task list |  | Project CNC-Foam cutter
[5 empty] | How long (days) |  |  |  | Comment column
Task ID | What | Who | Start | Finish | Fast | Slow | Most likely | Actual
1 | Decide wire material | 3 | 2011-03-22 | 2011-03-22 | 1 | 3 | 1 | 1
2 | Obtain wire | 3 | 2011-03-22 | 2011-03-22 | 2 | 6 | 5 | 1
3 | Test wire on foam | 1 | 2011-03-28 | 2011-03-23 | 1 | 3 | 2 | 2
4 | Set up stepper with motor controls | 4 | 2011-03-22 | 2011-03-22 | 5 | 7 | 6 | 1 |  | Hardware
5 | Test stepper motors | 4 | 2011-03-28 | 2011-03-23 | 1 | 3 | 2 | 2 |  | Elecronics
6 | Decide gearing | 1 | 2011-03-29 | 2011-03-23 | 1 | 3 | 2 | 2 |  | Software
7 | Obtain 3 more motors and controls | 4 | 2011-03-23 |  | 5 | 8 | 6
8 | Obtain lead screws | 3 | 2011-03-11 |  | 10 | 15 | 12
9 | Design spring mechanism | 2 | 2011-03-22 |  | 2 | 5 | 3 |  |  | Everybody | 1
10 | Design final version of movement plane | 2 | 2011-03-22 |  | 4 | 9 | 6 |  |  | Kristján | 2
11 | Design final assembly of machine. | 1 | 2011-03-25 |  | 4 | 7 | 6 |  |  | Sveinn | 3
[10 empty] | Fannar | 4
[10 empty] | outsourced | 5
Risk Assesment
Risk level
5
|  | 4 |  |  |  | T3 | T1
|  | 3 | O1
|  | 2 |  |  |  | T1 | F1
1
|  |  | 1 | 2 | 3 | 4 | 5 | Impact
|  | T1 | Unable to obtain lead screw
|  | F1 | Lead screws to expensive | [5 empty] | F= Financial
|  | T2 | Unable to obtain wire | [5 empty] | T= Technical
|  | T3 | Motor control does not work | [5 empty] | O= Other
|  | O1 | Time schedule fails.