## Sheet1
Task list |  | Project CNC-Foam cutter
[5 empty] | How long (days) |  |  |  | Comment column
Task ID | What | Who | Start | Finish | Fast | Slow | Most likely | Actual
1 | Deside rough dimensions | 1 | 2011-03-11 | 2011-03-17 | 3 | 8 | 6 | 6 | collaberate with Leifur | Hardware
2 | Conceptal CAD-model | 2 | 2011-03-11 | 2011-03-21 | 3 | 10 | 8 |  |  | Elecronics
3 | Find approriate lead screws | 3 | 2011-03-11 |  | 10 | 15 | 12 |  |  | Software
4 | Find suitable steppers | 1 | 2011-03-11 |  | 4 | 15 | 12
5 | Motors control | 4 | 2011-03-11 |  | 4 | 15 | 12
6 | Test phase and deside gearing | 1 | 2011-03-23 |  | 2 | 5 | 3 |  |  | Everybody | 1
7 | Final design | 1 | 2011-03-23 |  | 2 | 5 | 4 |  |  | Kristján | 2
8 | Get material | 2 | 2011-03-27 |  | 1 | 3 | 2 |  |  | Sveinn | 3
9 | Build component | 1 | 2011-03-28 | ? |  |  |  |  | We will problably not finish | Fannar | 4
10 | Obtain control unit ( Arduino) | 2 | ? | [5 empty] | We will problably not start | outsourced | 5
11 | Program Arduino to move steppers | 2 | ?
12 | Obtain hot wire + components | 4 | ?
13 | Assembly | 3 +4 | ?
14 | Preliminary Test | 1 | ?
15 | Advanced programming | 5 | ?
16 | Testing | 1 +5 | ?
17 | Final revision | 1 +5 | ?